## Sheet1
User Story-4 Password Reset Functionality
Test Cases | Name | Type | Status | Tested By
Test 4.1 | Verify the "Forgot Password" form is displayed and captures the user's email. | Unit Test | Passed | Jay, 10/15/2024
Test 4.2 | Validate that an invalid email prompts an error message. | Unit Test | Passed | Jay, 10/15/2024
Test 4.3 | Ensure the system allows the user to update the password after email verification. | Integration Test | Passed | Jay, 10/16/2024
Test 4.4 | Confirm the updated password is stored correctly in the database. | Integration Test | Passed | Jay, 10/16/2024
User Story 5 - Activation Link for New Users
Test Cases | Name | Type | Status | Tested By
Test 5.1 | Verify that the activation link is generated upon registration. | Unit Test | Passed | Jay, 10/18/2024
User Story 6 - Product Categorization
Test Cases | Name | Type | Status | Tested By
Test 6.1 | Check the database structure for storing product categories is correctly designed. | Unit Test | Passed | Harshavardhan, 10/21/2024
Test 6.2 | Validate that the UI displays the correct product categories to the user. | Integration Test | Passed | Harshavardhan, 10/22/2024
Test 6.3 | Ensure products are fetched and displayed based on the selected category. | Integration Test | Passed | Harshavardhan, 10/23/2024
User Story 7 - Product Search
Test Cases | Name | Type | Status | Tested By
Test 7.1 | Verify the search functionality returns results based on user input. | Unit Test | Passed | Harshavardhan, 10/23/2024
Test 7.2 | Check the results page displays the correct product information | Integration Test | Passed | Harshavardhan, 10/23/2024
User Story 8 - Shopping Cart
Test Cases | Name | Type | Status | Tested By
Test 8.1 | Ensure products can be added to the shopping cart via the "Add to Cart" button. | Unit Test | Passed | Bhargav, 10/24/2024
Test 8.2 | Validate the shopping cart system correctly stores and displays selected products | Integration Test | Passed | Bhargav, 10/24/2024
Test 8.3 | Confirm the user can manage items in the cart (e.g., remove, update quantity). | Integration Test | Passed | Bhargav, 10/24/2024